## Sheet1
Freemantle Park Income and Expenditure
Dowry Received | 6125 | Expenditure Discription | Cost + VAT | Status
|  | Post Strimmer Guards | 287 | Completed
|  | Weed removal/strimming of childrens play area | Free | Completed
|  | Refurbishment of goal posts | 120 | Completed
|  | Clearance of scrub adjacent to entrance from Enbrook Road | 480 | Completed | Additional chippings delivered/spread by Harmers 11/1/21 at nil cost
|  | Clearance of scrub adjacent to 5 a side pitch | 150 | Completed
|  | Stickly temporary signs advising now maintained by us with contact details | 80 | Completed
|  | Dog poo bag dispenser + installation | 52 | Completed
|  | Refurbishment to Childrens play equipment/bench | 550 | Completed
|  | Fremantle Fliers | 70 | Completed
|  | To dig out the gaps in the surface in the play area, supply and fill with Granules, and wetpour, together with all the other things like primer and edge binder. | 620 | Completed | Defer to early Spring 2021
|  | Slope - remove tree roots & install post & rail + 2 signs | 445 | Completed
|  | Replacement Tree - Tibetan Cherry Issue from Tree Inspection Report | 230 | Completed
|  | Removal of dead Cherry Tree Identified by Tree Inspection Report | 120 | Completed
|  | Remove mesh tree guard and slacken off tree ties enough so as to still provide support to the young tree. Remove allepicormic growth to a height of 1.5 meters above ground level. Replace mesh tree guard. Identified by Tree Inspection Report. | 40 | Completed
|  |  | 3244 | Running total
Possible expenditure yet to be considered/discussed:
|  | To prepare the slope from the park, supply and install sleeper steps, wooden edged and infill with recycled road plannings | 920 | Quote Received/ Not procceding
Having looked into this subject in some depth !!!!
|  | Basket Ball Post & Net. There are some cheap ones available, but the quality shows. | 850 | Quote Received
Therefore I feel to provide a good metal stand, complete with a back board and hoop. Concreted in the ground (in the grass area)
|  | 15/7 Telephone call received from Mr Hussain who lives at 55 Enbrook Valley 01303 487902 requesting we trim the trees in the park which are overhanging his Garden. | 360 | Quote Received/Approved by Resouces | RFO to speak with Mr Hussain - no success.
Quote from Harmers received 3/8 following site visit and discussion with Mr Hussain. In addition to work for this year annual cut back will be required £180/200
|  | 11/8 To install bench (not supplied) | 100 | Quote Received
|  | 1/2021 To Service new waste bin | 94.23 | Approved by RFO as under £200
|  | Annual Grounds Maintenance Costs | 2500
Box of Standard Dog Poo bags £26 (price at July 2020) say one every two months
Annual trim of trees adjacent to 55 Enbrook Valley £180/£200. Price quoted Aug 2020
25/6 RFO Summary: Assuming 6 months of annual grounds maintenance costs £1250 + confirmed costs todate of £3244 we will have spent £4,494 + Dog bags. Dowry was £6,125.00
15/7 Box of poo bags delivered to Michelle Pitcher 220 Shorncliffe Road
17/9 Box of poo bags delivered to Michelle Pitcher 220 Shorncliffe Road