## Sheet1
Ref | Title | Description | Proposer | Current Status | Action | Who to lead action | Priority | Other Comments
1 | Public realm: provide a first-class public environment which promotes community use and supports a diverse and vibrant business community | Introduction of solar panels onto assets for clean, renewable energy, starting with the Boat House to provide the Boat House and the toilet block main power supply - with signage/displays showing how effective it is/what it's generating/what it's saving | Annual Plan | Gaye is getting third quote | Review once have all quotes | Tim & Gaye | High
2 |  | "Solarium" area by the Moore Memorial - need to decide what this underused space should be, and use it as a facility e.g fill it to one steps depth with sand and create a big kiddie sandpit with surrounding seating, and possibly a marked "trading" bay in the area the other side of it (which we could rent to an ice-cream van / coffee trailer etc) to bring more life | Tim |  | Develop ideas for discussion | Rosa & Gaye | High
3 |  | Ensure all land management contractors have Health and Safety and RoSPA training and appropriate equipment to ensure that assets are maintained in optimal condition | Annual Plan |  | Watching brief | Hazel
4 |  | Continue to liaise with caretaking staff to identify any issues which would diminish customer satisfaction or impede usage of the recreation areas | Annual Plan |  | Ongoing | Gaye
5 |  | Investigate possible partnership working and sponsorship opportunities to enhance the provision of play equipment, seating and structures in parks and open areas | Annual Plan |  | Gaye applying for Lottery Funding (£20k in September) | Gaye | Medium
6 |  | Partnership working with the Sandgate Environmental Group to schedule regular litter picking of the area and beach | Annual Plan |  | Ongoing liaison | Hazel
7 |  | Renewal of caretaker and grounds maintenance contracts, expanding their scope and any additions / deletions / review prior to retendering | Annual Plan | Contract up for renewal April 2024 | Review at the end of the year - Fremantle needs to be added | To be decided | Medium
8 | Transport: to ensure improved safety on all streets of Sandgate for all users and to ensure walking, wheeling and cycling are safe and attractive choices for short journeys in/to the Parish | Advocate residents’ and businesses’ views on parish traffic management and parking to all responsible authorities | Annual Plan |  | Watching brief | Susan
9 |  | Produce a live Highways Improvement Plan and ensure that all instances of misuse of the highways are actively reported and reviewed for response | Annual Plan | Current HIP was reviewed by KCC in the Spring | Ongoing | Hazel and Susan
10 |  | Continue to campaign for 20 is Plenty on all parish roads, working in concert with local businesses and schools to achieve greater road safety, particularly on the A259 | Annual Plan | Part of the HIP - KCC has said | Use of the 30mph toolkit? | Susan | High
11 |  | Identify missing dropped kerbs in Enbrook Valley | Tim | In HIP | Identify where more would improve walking routes and lobby KCC for them | Nicola - with Street Monitors (when decided) | Medium
12 |  | Enbrook Valley Road (near Fremantle Park) has a zero kerb delineation up one side, leading to cars often driving up the pavement right in front of people's paths - need bollards to prevent this | Tim/HIP | Tim had KCC close to installing bollards and a line to make it clearer, but that seems to have stalled | Gaye to chase KCC | Tim & Gaye | Medium | KCC to contact Clive Lofting to discuss (taken over from Kieran Greenway)
13 |  | High Street zebra crossing safety concerns with visibility and vehicles not stopping | HIP | Upgrade deemed not feasible by KCC | Build out? Site visit to discuss options (and also look at Zebra by Sandgate Hotel) | Susan | Medium
14 |  | Between 99 High Street and Tower Court - no dropped kerbs, shingle - makes crossing difficult/impossible | HIP | Difficult to install a dropped kerd due to utilities | Look at as part of site visit - have a raised crossing (Copenhagen crossing)? | Susan | Medium | KCC contacting Clive Lofting to discuss
15 |  | Identify junctions which are difficult to cross and could be improved e.g. Military Road at junction with Sandgate High St; Coolinge Lane at junction with Sandgate Hill | Susan |  | Identify junctions with Street Wardens and progress improvements | Susan | Medium
16 |  | Identidy options to enhance cycle parking e.g. in Council car parks, at the front of the Library, on Sandgate High St | Susan |  | Identify locations with Street Wardens | Susan
17 |  | Escarpment walking routes are poorly signposted as to destination and often badly made | Tim | They need improving (the developer owner should do it) | Gaye to remind the developers | Gaye
18 | Environmental issues: improving biodiversity, monitoring seawater quality and reducing flooding and noise | Sea water quality testing - Environment Agency "Sandgate" testing point is pretty much Seabrook - would be better testing water at Granville Parade (by the overflow) | Tim | Tim emailed Ewan Green (F&HDC) on 10 July about the best way to progress this | Need to source testing kits and a common methodology would be good - await advice from F&HDC or progress ourselves directly - could cost about £600 and would need approval | Peter | High
19 |  | Wilding e.g. Battery Point wall/the Esplanade maintenance - are we are maintaining them right, or could we be doing something to allow more species diversity. Also both parks - e.g. Enbrook Park - large area to the south (at the bottom) - ideal location for a wildflower meadow (with mown paths) | Tim | We have always gone "tidy" | Introduce some "wilder" areas - maybe along the sea wall, with a cut verge at the front or in bits of our parks etc | Guy | Medium
20 |  | Tree planting - correspondence with Cyma Architects about planting trees in Sandgate to offset the ones lost in the development on Military Road |  | Need to suggest locations | Meeting on Thursday 13 July 2023 then follow up on locations |  | Medium
21 |  | Sustainable Urban Drainage - encourage the provision of planting/rain gardens to improve drainage and run-off | Susan | Ongoing through Planning Applications, but also need to look for other opportunities |  | Guy and Planning Committee and Susan
22 |  | Monitor street drains for blockages. Perhaps get a few "jackets" or something marked up with "Sandgate Street Inspection" or similar | Tim |  | Make part of "street monitoring" | Street Monitors
23 |  | Noise - problem of noise from motorbikes in the Valley | Peter |  | Gaye to contact F&HDC | Peter & Gaye
24 |  | Aim to be a carbon neutral council - we would need to benchmark ourselves first to judge current usage then a route to reduce | Tim |  |  | Tim
25 | Local services: to achieve and develop on successful liaison with local services for the benefit of the local community, businesses and visitors | Effectively monitor local service providers to improve the customer experience | Annual Plan | There is a directory of local services on the website | Review and update directory and promote with new and existing businesses to help signposting of services | Rosa
26 |  | Liaise with the beach management team to ensure that the annual beach replenishment programme is factored into any parish plans for beachside activities and avoid disappointment to stakeholders | Annual Plan | District informed - not the Parish | Seek improved communication | Tim & Gaye
27 |  | Ensure that all facilities, and public areas are clean and safe, liaising with all utility providers monthly to highlight possible omissions or areas for improvement | Annual Plan |  | Ongoing | Street Monitors
28 | Community Integration and Inclusion | The Shorncliffe development is in large part in Sandgate, but doesn't look to it, or currently feel it. We need to get some sense of it as "Upper Sandgate" and bond them into our community. | Tim |  | Tim to be Street Champion - and more to be done | Tim | Medium
29 |  | Make the library more of a community facility - how can we get it open more evenings and weekends - not necessarily as a library, but as a club space, learning space, meeting space, engagement area? | Tim |  |  | Events & Library Committee
30 |  | More diverse community involvement - we're reasonably engaging (the library helps) but we could do much better: schools and young people in particular, but the homebound/disabled too, and those with English as a second language | Tim |  |  | Rosa
31 | Community Safety: to ensure that the health and safety of all the community is prioritised and to improve awareness of life saving strategies | Ensure the safety of parish residents and businesses is at the forefront of local police and PCSO priorities and activities | Annual Plan |  | Ongoing
32 |  | Liaise with local police to provide an ongoing series of community safety events, including development of neighbourhood watch scheme | Annual Plan |  | Ongoing | Hazel
33 |  | Ensuring that all Health and Safety protocols are strictly adhered to at all events and activities | Annual Plan |  | Ongoing | Events and Sea Festival Committee
34 |  | Engaging the RNLI to produce a display promoting safe seaside practices and protocols | Annual Plan | Display at Sea Festival | Assess scope for permanent display and wording on jet skis etc | Gaye | Medium
35 |  | Provide an ongoing series of defibrillator training with the service provider for all staff and include all local businesses in the offer | Annual Plan |  | Training to be arranged | Gaye | Medium